## 05-10-2023
Daily Progress Report of Malanjkhand Copper Project
2023-07-20
Sl.No |  |  | Target |  | Progress |  |  | Remarks (if any)
|  | UNITS | For the month | For the day | For the day | For the month | Cumulative for the year
OVERALL PERFORMANCE
1 | Total Open Pit Excavation | Cubic Meter | 1000 | 32.2581 | 32 | 610.31 | 22965.56
2 | Total Open Pit Ore | Tonnes | 30000 | 967.7419 | 0 | 26460 | 893640
3 | Total Development Ore - UG | Tonnes | 8510 | 274.5161 | 0 | 0 | 29526
4 | Total Production Ore - UG | Tonnes | 560 | 25 | 150 | 6500 | 35699
5 | TOTAL ORE FROM MINE (2+3+4) | Tonnes | 39070 | 1267.2581 | 150 | 32960 | 958865
6 | Ore Grade (%Cu) | (%) | 0.9 | 0.9 | 0.85 | 0.89 | 0.915
7 | Crushing | Tonnes | 11450 | 369.3548 | 130.6 | 3306.795 | 43551.555
8 | Milling | Tonnes | 75000 | 2419.3548 | 3023.5 | 52144.1 | 43552.555
9 | Concentrate (WMT) | Tonnes | 75000 | 2419.3548 | 1701.2 | 47859.35 | 43553.555
10 | MIC | Tonnes | 150000 | 4838.7097 | 4724.7 | 100003.45 | 43554.555
11 | Concentrate Dispatched (WMT) | Tonnes | 75000 | 2419.3548 | 3023.5 | 52144.1 | 43555.555
CONTRACTUAL PERFORMANCE
A | SMSL PRODUCTION CONTRACT
1 | Total Development | meters | 1000 | 32.2581 | 32 | 610.31 | 22965.56
2 | Trough drilling in m | meters | 8510 | 274.5161 | 0 | 0 | 29526
3 | Production drilling in m | meters | 17790 | 573.871 | 172 | 8486.195 | 46676.075
CONTRACTUAL PERFORMANCE
B | NORTH DEVELOPMENT CONTRACT
1 | Total Development | meters | 400 | 12.9032 | 3023.5 | 52144.1 | 789915.85
2 | Decline -Development | meters | 200 | 6.4516 | 1701.2 | 47859.35 | 789916.85
3 | Horizontal Development | meters | 150 | 4.8387 | 4724.7 | 100003.45 | 789917.85
4 | Vertical Development | meters | 95 | 3.0645 | 4724.7 | 100003.45 | 789918.85
5 | Associated Development | meters | 125 | 4.0323 | 4724.7 | 100003.45 | 789919.85
CONTRACTUAL PERFORMANCE
C | SOUTH DECLINE DEVELOPMENT
1 | Total Development | meters | 400 | 12.9032 | 3023.5 | 52144.1 | 789915.85
2 | Decline -Development | meters | 200 | 6.4516 | 1701.2 | 47859.35 | 789916.85
3 | Horizontal Development | meters | 150 | 4.8387 | 4724.7 | 100003.45 | 789917.85
4 | Vertical Development | meters | 95 | 3.0645 | 4724.7 | 100003.45 | 789918.85
5 | Associated Development | meters | 125 | 4.0323 | 4724.7 | 100003.45 | 789919.85