## Sheet1
Unit | Mines | Contractor | Sl | Task | BoQ Qty | Work Completed Qty | Issue of LOI | Mobilisation | Start Date | End Date | Duration (Days) | Actual Start | Actual End | Days Remaining | Progress | Budget | Consumed | Remaining | Target Qty | Days till Today | Target %age | Today | Data_date
MCP | Mines O/C | Contract 01 | 1 | Master Schedule | 15847 | 14452 | 2022-06-10 | 2022-10-08 | 08/10/2022 | 22/09/2025 | 1080 | 13/10/2022 | 27/09/2025 | 620 | 71.69% | 33300000 | 23874098.3607 | 9425901.6393 | 14648.5972 | 465 | 92.44% | 2024-01-16 | 2024-01-16
MCP | Mines O/C | Contract 01 | 1.1 | Decline Development | 1241 | 1241 |  |  | 2022-10-08 | 2023-08-04 | 300 | 2022-10-13 | 2023-08-09 | 0 | 100% | 3000000 | 3000000 | 0 | 1241 | 300 | 100% | 2024-01-16 | 2024-01-16
MCP | Mines O/C | Contract 01 | 1.2 | Ramp from -60 mRL to -110 mRL | 330 | 0 |  |  | 2024-09-27 | 2025-06-24 | 270 | 2024-10-02 | 2025-06-29 | 525 | 0% | 2500000 | 0 | 2500000 | 0 | 0 | 0% | 2024-01-16 | 2024-01-16
MCP | Mines O/C | Contract 01 | 1.3 | Associated Dev. (LB, level sump, Cross over, Subsection) | 650 | 650 |  |  | 2022-10-08 | 2023-01-06 | 90 | 2022-10-13 | 2023-01-11 | 0 | 100% | 10000000 | 10000000 | 0 | 650 | 90 | 100% | 2024-01-16 | 2024-01-16
MCP | Mines O/C | Contract 01 | 1.4 | Horizontal Developments | 11735 | 11735 |  |  | 2022-10-08 | 2023-10-03 | 360 | 2022-10-13 | 2023-10-08 | 0 | 100% | 3400000 | 3400000 | 0 | 11735 | 360 | 100% | 2024-01-16 | 2024-01-16
MCP | Mines O/C | Contract 01 | 1.5 | Conveyor Driver | 366 | 366 |  |  | 2023-10-03 | 2023-11-02 | 30 | 2023-10-08 | 2023-11-07 | 0 | 100% | 5900000 | 5900000 | 0 | 366 | 30 | 100% | 2024-01-16 | 2024-01-16
MCP | Mines O/C | Contract 01 | 1.6 | Vertical Development | 1525 | 460 |  |  | 2022-10-08 | 2025-09-22 | 1080 | 2022-10-13 | 2025-09-27 | 615 | 30.16% | 8500000 | 2563934.4262 | 5936065.5738 | 656.5972 | 465 | 43.06% | 2024-01-16 | 2024-01-16
MCP | Mines U/C | Contract 02 | 2 | Master Schedule | 21831 | 9610 | 2023-02-19 | 2023-06-19 | 19/06/2023 | 03/06/2026 | 1080 | 19/06/2023 | 03/06/2026 | 869 | 37.59% | 24300000 | 9134791.7483 | 15165208.2517 | 11886.8611 | 211 | 54.45% | 2024-01-16 | 2024-01-16
MCP | Mines U/C | Contract 02 | 2.1 | Decline Development | 1545 | 950 |  |  | 2023-06-19 | 2024-04-14 | 300 | 2023-06-25 | 2024-04-20 | 89 | 61.49% | 1500000 | 922330.0971 | 577669.9029 | 1086.65 | 211 | 70.33% | 2024-01-16 | 2024-01-16
MCP | Mines U/C | Contract 02 | 2.2 | Ramp from -60 mRL to -110 mRL | 550 | 0 |  |  | 2025-06-08 | 2026-03-05 | 270 | 2025-06-11 | 2026-03-08 | 779 | 0% | 1000000 | 0 | 1000000 | 0 | 0 | 0% | 2024-01-16 | 2024-01-16
MCP | Mines U/C | Contract 02 | 2.3 | Associated Dev. (LB, level sump, Cross over, Subsection) | 750 | 750 |  |  | 2023-06-19 | 2023-09-17 | 90 | 2023-06-25 | 2023-09-23 | 0 | 100% | 8500000 | 8500000 | 0 | 750 | 90 | 100% | 2024-01-16 | 2024-01-16
MCP | Mines U/C | Contract 02 | 2.4 | Horizontal Developments | 16456 | 7550 |  |  | 2023-06-19 | 2024-06-13 | 360 | 2023-06-27 | 2024-06-21 | 149 | 45.88% | 1900000 | 871718.5221 | 1028281.4779 | 9645.0444 | 211 | 58.61% | 2024-01-16 | 2024-01-16
MCP | Mines U/C | Contract 02 | 2.5 | Conveyor Driver | 550 | 0 |  |  | 2024-01-15 | 2024-02-14 | 30 | 2024-01-19 | 2024-02-18 | 29 | 0% | 4400000 | 0 | 4400000 | 18.3333 | 1 | 3.333% | 2024-01-16 | 2024-01-16
MCP | Mines U/C | Contract 02 | 2.6 | Vertical Development | 1980 | 360 |  |  | 2023-06-19 | 2026-06-03 | 1080 | 2023-06-19 | 2026-06-03 | 869 | 18.18% | 7000000 | 1272727.2727 | 5727272.7273 | 386.8333 | 211 | 19.54% | 2024-01-16 | 2024-01-16
ICC | SUDRA MINES | Contract 03 | 3 | Master Schedule | 14395 | 12805 | 2022-08-10 | 2022-12-08 | 08/12/2022 | 22/11/2025 | 1080 | 08/12/2022 | 02/12/2025 | 678 | 71.75% | 21300000 | 15282085.5615 | 6017914.4385 | 12934.5185 | 404 | 89.85% | 2024-01-16 | 2024-01-16
ICC | SUDRA MINES | Contract 03 | 3.1 | Decline Development | 1050 | 1050 |  |  | 2022-12-08 | 2023-10-04 | 300 | 2022-12-08 | 2023-10-19 | 0 | 100% | 1000000 | 1000000 | 0 | 1050 | 300 | 100% | 2024-01-16 | 2024-01-16
ICC | SUDRA MINES | Contract 03 | 3.2 | Ramp from -60 mRL to -110 mRL | 290 | 0 |  |  | 2024-11-27 | 2025-08-24 | 270 | 2024-11-27 | 2025-09-08 | 586 | 0% | 500000 | 0 | 500000 | 0 | 0 | 0% | 2024-01-16 | 2024-01-16
ICC | SUDRA MINES | Contract 03 | 3.3 | Associated Dev. (LB, level sump, Cross over, Subsection) | 870 | 870 |  |  | 2022-12-08 | 2023-03-08 | 90 | 2022-12-08 | 2023-03-23 | 0 | 100% | 8000000 | 8000000 | 0 | 870 | 90 | 100% | 2024-01-16 | 2024-01-16
ICC | SUDRA MINES | Contract 03 | 3.4 | Horizontal Developments | 9860 | 9860 |  |  | 2022-12-08 | 2023-12-03 | 360 | 2022-12-08 | 2023-12-11 | 0 | 100% | 1400000 | 1400000 | 0 | 9860 | 360 | 100% | 2024-01-16 | 2024-01-16
ICC | SUDRA MINES | Contract 03 | 3.5 | Conveyor Driver | 455 | 455 |  |  | 2023-07-06 | 2023-08-05 | 30 | 2023-07-06 | 2023-08-20 | 0 | 100% | 3900000 | 3900000 | 0 | 455 | 30 | 100% | 2024-01-16 | 2024-01-16
ICC | SUDRA MINES | Contract 03 | 3.6 | Vertical Development | 1870 | 570 |  |  | 2022-12-08 | 2025-11-22 | 1080 | 2022-12-08 | 2025-12-02 | 676 | 30.48% | 6500000 | 1981283.4225 | 4518716.5775 | 699.5185 | 404 | 37.41% | 2024-01-16 | 2024-01-16
ICC | KENDADIH MINE | Contract 04 | 4 | Master Schedule | 22686 | 16150 | 2022-12-10 | 2023-04-09 | 09/04/2023 | 24/03/2026 | 1080 | 14/04/2023 | 24/03/2026 | 800 | 63.34% | 116800000 | 73986614.7979 | 42813385.2021 | 17098.5667 | 282 | 75.37% | 2024-01-16 | 2024-01-16
ICC | KENDADIH MINE | Contract 04 | 4.1 | Decline Development | 1980 | 1650 |  |  | 2023-04-09 | 2024-02-03 | 300 | 2023-04-14 | 2024-02-03 | 0 | 83.33% | 13500000 | 11250000 | 2250000 | 1861.2 | 282 | 94% | 2024-01-16 | 2024-01-16
ICC | KENDADIH MINE | Contract 04 | 4.2 | Ramp from -60 mRL to -110 mRL | 488 | 0 |  |  | 2025-03-29 | 2025-12-24 | 270 | 2025-04-03 | 2025-12-24 | 708 | 0% | 6900000 | 0 | 6900000 | 0 | 0 | 0% | 2024-01-16 | 2024-01-16
ICC | KENDADIH MINE | Contract 04 | 4.3 | Associated Dev. (LB, level sump, Cross over, Subsection) | 890 | 890 |  |  | 2023-04-09 | 2023-07-08 | 90 | 2023-04-14 | 2023-07-08 | 0 | 100% | 9400000 | 9400000 | 0 | 890 | 90 | 100% | 2024-01-16 | 2024-01-16
ICC | KENDADIH MINE | Contract 04 | 4.4 | Horizontal Developments | 16890 | 12560 |  |  | 2023-04-09 | 2024-04-03 | 360 | 2023-04-14 | 2024-04-03 | 78 | 74.36% | 12000000 | 8923623.4458 | 3076376.5542 | 13230.5 | 282 | 78.33% | 2024-01-16 | 2024-01-16
ICC | KENDADIH MINE | Contract 04 | 4.5 | Conveyor Driver | 650 | 650 |  |  | 2023-11-05 | 2023-12-05 | 30 | 2023-11-10 | 2023-12-05 | 0 | 100% | 56500000 | 56500000 | 0 | 650 | 30 | 100% | 2024-01-16 | 2024-01-16
ICC | KENDADIH MINE | Contract 04 | 4.6 | Vertical Development | 1788 | 400 |  |  | 2023-04-09 | 2026-03-24 | 1080 | 2023-04-14 | 2026-03-24 | 798 | 22.37% | 18500000 | 4138702.4609 | 14361297.5391 | 466.8667 | 282 | 26.11% | 2024-01-16 | 2024-01-16
KCC | KHETRI | Contract 05 | 5 | Master Schedule | 15847 | 9290 | 2023-01-10 | 2023-05-10 | 10/05/2023 | 24/04/2026 | 1080 | 20/05/2023 | 01/05/2026 | 831 | 53.56% | 52800000 | 28278247.556 | 24521752.444 | 10590.6274 | 251 | 66.83% | 2024-01-16 | 2024-01-16
KCC | KHETRI | Contract 05 | 5.1 | Decline Development | 1241 | 750 |  |  | 2023-05-10 | 2024-03-05 | 300 | 2023-05-20 | 2024-03-12 | 0 | 60.44% | 6250000 | 3777195.8098 | 2472804.1902 | 1038.3033 | 251 | 83.67% | 2024-01-16 | 2024-01-16
KCC | KHETRI | Contract 05 | 5.2 | Ramp from -60 mRL to -110 mRL | 330 | 0 |  |  | 2025-04-29 | 2026-01-24 | 270 | 2025-05-09 | 2026-01-31 | 739 | 0% | 5750000 | 0 | 5750000 | 0 | 0 | 0% | 2024-01-16 | 2024-01-16
KCC | KHETRI | Contract 05 | 5.3 | Associated Dev. (LB, level sump, Cross over, Subsection) | 650 | 650 |  |  | 2023-05-10 | 2023-08-08 | 90 | 2023-05-20 | 2023-08-15 | 0 | 100% | 13250000 | 13250000 | 0 | 650 | 90 | 100% | 2024-01-16 | 2024-01-16
KCC | KHETRI | Contract 05 | 5.4 | Horizontal Developments | 11735 | 7340 |  |  | 2023-05-10 | 2024-05-04 | 360 | 2023-05-20 | 2024-05-11 | 109 | 62.55% | 6650000 | 4159437.5799 | 2490562.4201 | 8181.9028 | 251 | 69.72% | 2024-01-16 | 2024-01-16
KCC | KHETRI | Contract 05 | 5.5 | Conveyor Driver | 366 | 300 |  |  | 2023-12-06 | 2024-01-05 | 30 | 2023-12-16 | 2024-01-12 | 0 | 81.97% | 9150000 | 7500000 | 1650000 | 366 | 30 | 100% | 2024-01-16 | 2024-01-16
KCC | KHETRI | Contract 05 | 5.6 | Vertical Development | 1525 | 250 |  |  | 2023-05-10 | 2026-04-24 | 1080 | 2023-05-20 | 2026-05-01 | 829 | 16.39% | 11750000 | 1926229.5082 | 9823770.4918 | 354.4213 | 251 | 23.24% | 2024-01-16 | 2024-01-16
KCC | BANWAS | Contract 06 | 6 | Master Schedule | 19271 | 201 | 2023-09-10 | 2024-01-08 | 08/01/2024 | 23/12/2026 | 1080 | 08/01/2024 | 23/12/2026 | 1074 | 1.675% | 61720000 | 1033882.0108 | 60686117.9892 | 433.8741 | 8 | 2.251% | 2024-01-16 | 2024-01-16
KCC | BANWAS | Contract 06 | 6.1 | Decline Development | 1345 | 25 |  |  | 2024-01-08 | 2024-11-03 | 300 | 2024-01-08 | 2024-11-03 | 0 | 1.859% | 18250000 | 339219.3309 | 17910780.6691 | 35.8667 | 8 | 2.667% | 2024-01-16 | 2024-01-16
KCC | BANWAS | Contract 06 | 6.2 | Ramp from -60 mRL to -110 mRL | 250 | 0 |  |  | 2025-12-28 | 2026-09-24 | 270 | 2025-12-28 | 2026-09-24 | 982 | 0% | 6734000 | 0 | 6734000 | 0 | 0 | 0% | 2024-01-16 | 2024-01-16
KCC | BANWAS | Contract 06 | 6.3 | Associated Dev. (LB, level sump, Cross over, Subsection) | 670 | 46 |  |  | 2024-01-08 | 2024-04-07 | 90 | 2024-01-08 | 2024-04-07 | 0 | 6.866% | 6234000 | 428005.9701 | 5805994.0299 | 59.5556 | 8 | 8.889% | 2024-01-16 | 2024-01-16
KCC | BANWAS | Contract 06 | 6.4 | Horizontal Developments | 14567 | 120 |  |  | 2024-01-08 | 2025-01-02 | 360 | 2024-01-08 | 2025-01-02 | 352 | 0.8238% | 13734000 | 113137.9145 | 13620862.0855 | 323.7111 | 8 | 2.222% | 2024-01-16 | 2024-01-16
KCC | BANWAS | Contract 06 | 6.5 | Conveyor Driver | 449 | 0 |  |  | 2024-08-05 | 2024-09-04 | 30 | 2024-08-05 | 2024-09-04 | 0 | 0% | 7134000 | 0 | 7134000 | 0 | 0 | 0% | 2024-01-16 | 2024-01-16
KCC | BANWAS | Contract 06 | 6.6 | Vertical Development | 1990 | 10 |  |  | 2024-01-08 | 2026-12-23 | 1080 | 2024-01-08 | 2026-12-23 | 1072 | 0.5025% | 9634000 | 48412.0603 | 9585587.9397 | 14.7407 | 8 | 0.7407% | 2024-01-16 | 2024-01-16
KCC | KOLIHAN | Contract 07 | 7 | Master Schedule | 23115 | 8355 | 2023-04-10 | 2023-08-08 | 08/08/2023 | 23/07/2026 | 1080 | 22/08/2023 | 01/08/2026 | 921 | 31.82% | 73720000 | 23454767.6463 | 50265232.3537 | 10015.4204 | 161 | 43.33% | 2024-01-16 | 2024-01-16
KCC | KOLIHAN | Contract 07 | 7.1 | Decline Development | 1790 | 755 |  |  | 2023-08-08 | 2024-06-03 | 300 | 2023-08-22 | 2024-06-12 | 0 | 42.18% | 30250000 | 12759078.2123 | 17490921.7877 | 960.6333 | 161 | 53.67% | 2024-01-16 | 2024-01-16
KCC | KOLIHAN | Contract 07 | 7.2 | Ramp from -60 mRL to -110 mRL | 445 | 0 |  |  | 2025-07-28 | 2026-04-24 | 270 | 2025-08-11 | 2026-05-03 | 829 | 0% | 6734000 | 0 | 6734000 | 0 | 0 | 0% | 2024-01-16 | 2024-01-16
KCC | KOLIHAN | Contract 07 | 7.3 | Associated Dev. (LB, level sump, Cross over, Subsection) | 890 | 890 |  |  | 2023-08-08 | 2023-11-06 | 90 | 2023-08-22 | 2023-11-15 | 0 | 100% | 6234000 | 6234000 | 0 | 890 | 90 | 100% | 2024-01-16 | 2024-01-16
KCC | KOLIHAN | Contract 07 | 7.4 | Horizontal Developments | 17670 | 6500 |  |  | 2023-08-08 | 2024-08-02 | 360 | 2023-08-22 | 2024-08-11 | 0 | 36.79% | 13734000 | 5052122.2411 | 8681877.7589 | 7902.4167 | 161 | 44.72% | 2024-01-16 | 2024-01-16
KCC | KOLIHAN | Contract 07 | 7.5 | Conveyor Driver | 560 | 0 |  |  | 2024-03-05 | 2024-04-04 | 30 | 2024-03-19 | 2024-04-13 | 0 | 0% | 7134000 | 0 | 7134000 | 0 | 0 | 0% | 2024-01-16 | 2024-01-16
KCC | KOLIHAN | Contract 07 | 7.6 | Vertical Development | 1760 | 210 |  |  | 2023-08-08 | 2026-07-23 | 1080 | 2023-08-22 | 2026-08-01 | 919 | 11.93% | 9634000 | 1149511.3636 | 8484488.6364 | 262.3704 | 161 | 14.91% | 2024-01-16 | 2024-01-16
Formulas:
Mobilisation = [Issue of LOI]+120
Days Remaining = [Actual End]-TODAY()
Days Remaining = [End Date]-TODAY()
Days till Today = IF(TODAY()-[Start Date]<0, "", IF(TODAY()-[Start Date]>[Duration (Days)], [Duration (Days)], TODAY()-[Start Date]))
Days till Today = IF(TODAY()-[Start Date]<=0, 0, IF(TODAY()-[Start Date]>[Duration (Days)], [Duration (Days)], TODAY()-[Start Date]))
Start Date = [Mobilisation, row above]
Start Date = [Start Date, row above]+(30*8*3)
End Date = [Start Date]+[Duration (Days)]
Actual Start = [Start Date]+5
Actual Start = [Start Date]
Actual End = [Actual Start]+[Duration (Days)]
Actual End = [Actual Start]+[Duration (Days)]+15

## Sheet2
Start Date
8-Oct-22
2022-10-08
2024-09-27
2022-10-08
2022-10-08
2023-10-03
2022-10-08
19-Jun-23
45096
45816
45096
45096
45306
45096
8-Dec-22
44903
45623
44903
44903
45113
44903
9-Apr-23
45025
45745
45025
45025
45235
45025
10-May-23
45056
45776
45056
45056
45266
45056
8-Jan-24
45299
46019
45299
45299
45509
45299
8-Aug-23
45146
45866
45146
45146
45356
45146

## Sheet3
Start Date | Start Date
8-Oct-22 | 8-Oct-22
2022-10-08 | 08-10-2022
2024-09-27 | 27-09-2024
2022-10-08 | 08-10-2022
2022-10-08 | 08-10-2022
2023-10-03 | 03-10-2023
2022-10-08 | 08-10-2022
19-Jun-23 | 19-Jun-23
2023-06-19 | 19-06-2023
2025-06-08 | 08-06-2025
2023-06-19 | 19-06-2023
2023-06-19 | 19-06-2023
2024-01-15 | 15-01-2024
2023-06-19 | 19-06-2023
8-Dec-22 | 8-Dec-22
2022-12-08 | 08-12-2022
2024-11-27 | 27-11-2024
2022-12-08 | 08-12-2022
2022-12-08 | 08-12-2022
2023-07-06 | 06-07-2023
2022-12-08 | 08-12-2022
9-Apr-23 | 9-Apr-23
2023-04-09 | 09-04-2023
2025-03-29 | 29-03-2025
2023-04-09 | 09-04-2023
2023-04-09 | 09-04-2023
2023-11-05 | 05-11-2023
2023-04-09 | 09-04-2023
10-May-23 | 10-May-23
2023-05-10 | 10-05-2023
2025-04-29 | 29-04-2025
2023-05-10 | 10-05-2023
2023-05-10 | 10-05-2023
2023-12-06 | 06-12-2023
2023-05-10 | 10-05-2023
8-Jan-24 | 8-Jan-24
2024-01-08 | 08-01-2024
2025-12-28 | 28-12-2025
2024-01-08 | 08-01-2024
2024-01-08 | 08-01-2024
2024-08-05 | 05-08-2024
2024-01-08 | 08-01-2024
8-Aug-23 | 8-Aug-23
2023-08-08 | 08-08-2023
2025-07-28 | 28-07-2025
2023-08-08 | 08-08-2023
2023-08-08 | 08-08-2023
2024-03-05 | 05-03-2024
2023-08-08 | 08-08-2023